## myTaxiService
Task Name | Start Date | End Date | Duration | Predecessors | Alessandro | Alberto | Francesco | Comments
RASD | 2015-10-07 | 2015-11-12 | 27d
T1 | 2015-10-07 | 2015-10-08 | 2d |  | X | X | X
T2 | 2015-10-09 | 2015-10-12 | 2d |  | X | X | X
T3 | 2015-10-13 | 2015-10-16 | 4d |  | X | X | X
T4 | 2015-10-17 | 2015-10-23 | 6d |  | X | X | X
T5 | 2015-10-24 | 2015-10-28 | 4d |  | X | X | X
T6 | 2015-10-29 | 2015-11-05 | 6d |  | X | X | X
T7 | 2015-11-06 | 2015-11-12 | 5d |  |  | X | X
DD | 2015-11-13 | 2016-01-14 | 45d
T8 | 2015-11-13 | 2015-11-30 | 12d |  | X | X
T9 | 2015-12-01 | 2015-12-11 | 9d |  | X | X
T10 | 2015-12-12 | 2015-12-22 | 8d |  | X | X
T11 | 2015-12-23 | 2016-01-05 | 10d |  | X | X | X
T12 | 2016-01-06 | 2016-01-14 | 7d |  | X | X | X
T13 | 2015-11-13 | 2015-12-17 | 25d |  |  |  | X
DEVELOPMENT | 2016-01-15 | 2016-05-30 | 97d
T14 | 2016-01-15 | 2016-02-04 | 15d |  | X |  | X
T15 | 2016-03-03 | 2016-03-24 | 16d |  | X |  | X
T16 | 2016-03-25 | 2016-04-25 | 22d |  | X | X | X
T17 | 2016-02-05 | 2016-03-02 | 19d |  | X |  | X
T18 | 2016-04-26 | 2016-05-30 | 25d |  | X | X | X
T19 | 2016-03-05 | 2016-03-24 | 15d |  |  | X
T20 | 2016-01-15 | 2016-02-09 | 18d |  |  | X
T21 | 2016-02-10 | 2016-03-04 | 18d |  |  | X
INTEGRATION TESTING | 2016-05-31 | 2016-07-05 | 26d
T22 | 2016-05-31 | 2016-06-15 | 12d |  | X | X | X
T23 | 2016-06-16 | 2016-07-05 | 14d |  | X | X | X
DEPLOYMENT | 2016-07-06 | 2016-07-11 | 4d
T24 | 2016-07-06 | 2016-07-11 | 4d |  | X | X | X

## Discussions
Row 1 | Discussion Title | Sample Discussion | Todd Jones | 08/28/13 8:58 PM
| Comments | Need help? E-mail us at support@smartsheet.com or call us at 425.283.1870 | Todd Jones | 08/28/13 8:58 PM
|  | This is a sample discussion. Discussions will let you track comments about a particular line item or sheet. Many customers paste relevant emails into a discussion as well. | Todd Jones | 08/28/13 8:59 PM